US216

Two Hours

UNIVERSITY OF MANCHESTER

INSTITUTE OF SCIENCE AND TECHNOLOGY

CT210 Software Quality

For candidates taking:

DEGREE OF BSc IN COMPUTATION

SECOND YEAR SESSIONAL

DEGREE OF BSc IN COMPUTING SCIENCE

SECOND YEAR SESSIONAL

DEGREE OF BSc IN INFORMATION SYSTEMS ENGINEERING

SECOND YEAR SESSIONAL

DEGREE OF BSc IN PURE MATHEMATICS AND COMPUTATION

SECOND YEAR SESSIONAL

DEGREE OF MEng, BEng IN SOFTWARE ENGINEERING

SECOND YEAR SESSIONAL

Friday 22 May 1998			2.00-4.00

Answer three questions - you MUST answer question 1 and any two other questions

Note: Do not answer more than the required number of questions.    Clearly cross out anything you do not wish to be marked

PTO

(2)

1)	(COMPULSORY)

Answer all parts

Write brief notes to describe the essential points of the following concepts.

(a)	Product and process quality

(b)	Software process maturity

(c)	Key process areas in the CMM (Capability Maturity Model)

(d)	Software risk

(e)	Defect prevention (as compared to defect detection)

(4 marks for each part, 20 marks in total)

US216

(3)

2)	Answer all parts

(a)	Briefly outline the objectives of the Requirements Management key process area which is found in level 2 of the CMM (Capability Maturity Model)

(3 marks)

(b)	Briefly describe the purpose Quality Function Deployment in the context of a software development project.

(3 marks)

(c)	Explain the purpose of an AHP (Analytical Hierarchy Process) matrix and how it is constructed.    An example of the matrix appears below and has been constructed for railway ticket issuing system.    Use this matrix in your answer.

|  | Standard single/ return tickets | Citizen charter refunds | Season tickets | Travelcards |  | Row total | Row average |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Standard single/return tickets | 0.60 | 0.29 | 0.71 | 0.33 |  | 1.92 | 0.48 |
| Citizen charter refunds | 0.09 | 0.04 | 0.03 | 0.01 |  | 0.17 | 0.04 |
| Season tickets | 0.20 | 0.29 | 0.24 | 0.60 |  | 1.32 | 0.33 |
| Travelcards | 0.12 | 0.38 | 0.03 | 0.07 |  | 0.59 | 0.15 |
| Column totals | 1.00 | 1.00 | 1.00 | 1.00 |  |  | 1.00 |

(7 marks)

(d)	Explain the purpose of a House of Quality and how it is constructed.    An example of a house of quality appears below and has been constructed for the above railway ticket issuing system- use it in your answer.

|  |  | Fare/refund calculation | Ticket printing | Auditing & security | User interface | Customer tracking |  | Sum | % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Standard single/return tickets | 48% | 9 | 7 | 3 | 1 | 0 |  | 20 | 19% |
| Citizen charter refunds | 4% | 5 | 1 | 7 | 5 | 3 |  | 21 | 20% |
| Season tickets | 33% | 7 | 7 | 3 | 9 | 7 |  | 33 | 31% |
| Travelcards | 15% | 7 | 7 | 3 | 9 | 5 |  | 31 | 29% |

(7 marks)

PTO

(4)

3)	Answer all parts

(a)	Briefly outline the objectives of the Software Project Planning and the Software Project Tracking and Oversight key process areas found in level 2 of the CMM (Capability Maturity Model).

(5 marks)

(b)	Lines of code (LOC) and function point counts (FPC)    are two measures of the size of a system.    Explain the advantages and disadvantages of using these two metrics for measuring systems.

(4 marks)

(c)	Produce a critical path network, showing the earliest start times and latest finish times for each task, using the data in the table below.    Write down the sequence of tasks on the critical path.

| Task code | Task name | Duration | Starts after completion of task number(s) |
| --- | --- | --- | --- |
| PLAN | Plan project | 3 |  |
| REQ | Capture requirements | 8 | PLAN |
| AGREE | Agree requirements with customer | 2 | REQ |
| DESIGN | Design system | 10 | AGREE |
| CODE | Code system | 12 | DESIGN |
| ID | Identify subcontractors | 3 | DESIGN |
| BUY | Buy-in subcontractor code | 5 | ID |
| INTEG | Integrate code and buy-in code | 6 | CODE, BUY |
| INFRA | Prepare infrastructure | 7 | AGREE |
| TRAIN | Train staff | 5 | INFRA |
| REL | Release system | 4 | INTEG, TRAIN |

(11 marks)

US216

(5)

4)	Answer all parts

(a)	Briefly outline the objectives of the Organisation Process Focus and the Organisation Process Definition key process areas found in level 3 of the CMM (Capability Maturity Model).

(5 marks)

(b)	Briefly describe the following process modelling notations

(i)	ETVX diagram

(ii)	IDEF diagram

(iii)	Role Activity Diagram

(iv)	RAEW matrix

(12 marks)

(c)	Briefly explain 3 types of problem which you might identify in any of the above 3 models.

(3 marks)

5)	Answer all parts

(a)	Explain the difference between testing code and conducting a peer review on a specification or requirements document.        Include in your answer an explanation as to why testing code alone is not sufficient to generate high quality software.    Comment on whether introducing peer reviews and testing will also be sufficient to generate high quality software.

(6 marks)

(b)	Explain the main factors to be considered when organising a peer review of a software deliverable.

(8 marks)

(c)	Give a reasoned explanation as to why peer review appears as a level 3 key process area in the CCM (Capability Maturity Model) and not level 2.

(6 marks)

END OF PAPER